## Slide 1: Facilities Update
Presented to:
Garden Grove Unified School District
Bond Oversight Committee
January 9, 2018
Presenters: Margaret Brown and Jerry Hills

## Slide 2
  Modernization and HVAC
  HVAC
  Seismic Replacement
  Projects in Planning
Overview

## Slide 3
    Ralston
    Bolsa Grande
    Los Amigos
    Santiago
Modernization & HVAC

## Slide 4
Ralston IS
Relocated office entry for increased security and added classroom space
Modernization & HVAC

## Slide 5
Bolsa Grande HS
More usable office space, efficient windows, new flagpole, HVAC units
Modernization & HVAC

## Slide 6
Los Amigos HS
Before and After - Admin offices looking from quad
Modernization & HVAC
New accessible doors, energy efficient windows and lighting

## Slide 7
Santiago HS
Before - Front of school
Modernization & HVAC

## Slide 8
Santiago HS
Inviting school front with added efficiency measures
Modernization & HVAC

## Slide 9
PACIFICA/LA QUINTA HIGH SCHOOL
Seismic Replacement
Buildings Phase 1 CR Construction – Summer 2016 Move In / Exis. Building Demo – Summer 2017
Phase 2 CR & Cafeteria Const. – Winter 2017 Move In / Exis. Building Demo – Winter 2018 Theatre & Library Media – Winter 2018 Completion – Fall 2019
Measure

## Slide 10
ANIMATION OF LA QUINTA
Measure

## Slide 11
Pacifica HS
Phase 1: New Classroom buildings occupied beginning 17-18 school year
Seismic Replacement
Measure

## Slide 12
Pacifica HS
Seismic Replacement
Measure
Phase 2: concrete footings and building interior slabs

## Slide 13
Seismic Replacement
Measure
Grading for Building Pads
La Quinta HS

## Slide 14
La Quinta HS
Seismic Replacement
Measure
Phase 2: New building exterior framing

## Slide 15
La Quinta HS
Seismic Replacement
Measure
Phase 2: New cafeteria steel framing

## Slide 16
  Hazard ES
  Heritage ES
  Rosita ES
  Wakeham ES
  Zeyen ES
HVAC projects Summer 2017
Measure

## Slide 17
Hazard ES
New ADA drop off, fencing for added security, flagpole, Windows and HVAC
HVAC
Measure

## Slide 18
Heritage ES
New windows, roofing, HVAC, flagpole, fencing, landscape, modern building finish
HVAC
Measure

## Slide 19
Rosita ES
New Classroom Casework, Windows, Lighting, & Dropped Ceiling
HVAC
Measure

## Slide 20
Wakeham ES
New Office Location and Secure Entry
HVAC
Measure

## Slide 21
Zeyen ES
New front entry and Secure campus entry
HVAC
Measure

## Slide 22
Santiago Gym Floor & Bleacher
Santiago Pool Repairs
Athletic Improvements
Measure

## Slide 23
Santiago HS
Gym Floor and Bleachers
Measure
Before

## Slide 24
Gym Floor and Bleachers
Measure
Sub floor in place, court surface staging
Santiago HS

## Slide 25
Gym Floor and Bleachers
Measure
New Floor and Bleachers
Santiago HS

## Slide 26
Pool
Measure
New Pool Plaster, lighting, tiles and coping
Santiago HS

## Slide 27
HVAC projects 2018 and beyond
Bolsa Building R (Insurance claim)
Bolsa Stadium
Seismic Gym Locker Buildings & Pool
Other projects in planning
Measure

## Slide 28
HVAC
  19 projects
  All plans have been submitted to DSA for approval
  To be completed over 3 Summers
  LLB negotiations to begin In October
  Anticipated Award Dec. 2017
Other projects in planning
Measure

## Slide 29
Bolsa Building R (insurance claim)
  Reconstruction deemed futile effort
  New building to be constructed
  Plans DSA approved
  Proposals due late January
Other projects in planning
Measure

## Slide 30
Bolsa Stadium
  Will be similar to Monsoor
  Currently in early planning stages
  Construction start: December 2018
Other projects in planning
Measure

## Slide 31
Seismic Gym Locker Buildings
  Pacifica and LQ
  DSA Approved in September
  Funding applications in process for up to 50% match
  Gymnasium, Locker Rooms, Pool
Other projects in planning
Measure

## Slide 32
La Quinta HS
Measure

## Slide 33
La Quinta HS
Measure

## Slide 34
La Quinta HS
Measure

## Slide 35
Measure
Pacifica HS

## Slide 36
QUESTIONS

## Slide 37
Facilities Update
Thank You!